## Sept 2026
Inspection Plan _ QA/QC SENA
No | Nama | Jabatan | Deskripsi Pekerjaan
|  |  | W2 (Sept 05 ~ 11) |  | W3 (Sept 12 ~ 18) |  | W4 (Sept 19 ~ 25) |  | W5 (Sept 26 ~ Oct 02)
|  |  | Area | Detail Pekerjaan | Area | Detail Pekerjaan | Area | Detail Pekerjaan | Area | Detail Pekerjaan
1 | Agus Parwedi | Civil & Structure Inspector | SWI | 1). L2512/RFI/PDP/CV/00418 Closed Punch List Cofferdum : Capping Beam Shoreline, Capping Beam Cofferdam, Fence, Handrail Cofferdam, Wall Cofferdam Segment 1, Wall Cofferdam Segment 2, Wall Cofferdam Segment 3, Wall Cofferdam Segment 4 & Rock Protection Shoreline 2). Review Dokumen RFI Project Pekerjaan Perbaikan Shoreline dan Cofferdam Sea Water Intake RDMP RU V Balikpapan PT PDP | SWI | 1). L2512/RFI/PDP/CV/00418 Closing Punch List Cofferdam : Capping Beam Shoreline, Capping Beam Cofferdam, Fence, Handrail Cofferdam, Wall Cofferdam Segment 1, Wall Cofferdam Segment 2, Wall Cofferdam Segment 3, Wall Cofferdam Segment 4 & Rock Protection Shoreline 2). Review Dokumen RFI Project Pekerjaan Perbaikan Shoreline dan Cofferdam Sea Water Intake RDMP RU V Balikpapan PT PDP 3). Monitoring Closing Punch List Cofferdam Capping Beam Shoreline, Capping Beam Cofferdam, Fence, Handrail Cofferdam, Wall Cofferdam Segment 1, Wall Cofferdam Segment 2, Wall Cofferdam Segment 3, Wall Cofferdam Segment 4 & Rock Protection Shoreline
2 | Adi Purwanto | Civil & Structure Inspector | OC-O | 1). Pouring Concrete Wall Basin Tahap (2) Segmen 1,2 & 3 2). Pouring Concrete Top Slab Basin Tahap (2) Segmen 2 & 3 3). Inspection Installation Waterstop Construction Joint 2 (Segmen 1-3) 4). Inspection of Anchor Bolt Installation (Lighting), Construction of the Retention Basin on Road 104 5). Remove Formwork All Segmen Tahap 2 Segmen 1,2 & 3 | OC-O | 1. Survey Anchor Cable Tray 2. Survey Anchor Platform Type-2 3. Bolt Tightening Anchor Cable Tray (7-10) 4. Grouting Pedestal Cable Tray (7-10) 5. Pouring Concrete Footing and Pedestal Platform Type-2 6. Pouring Concrete Slab Drainage B1-B2 7. Excavation Box Control CL-1 8. Before Concrete Pouring Lean Concrete Box Control CL-1 9. Pouring Concrete Lean Concrete Box Contrrol CL-1 10. Survey Excavation and Lean Concrete Box Control CL-1
|  |  | SWI | 1). Closing Panch List Cofferdum
3 | Achmad Agel Shahab | Civil & Structure Inspector | PIPE SUPPORT & PLATEFORM | 1). Operating Platform Installation at Tank A30, R-6, P5, A4, A5 2). Crossing Platform Installation at Tank R6 3). T-Post Installation at Tank R6 4). Concrete Compressive Strength Test for Pipe Support & Operating Platform Foundation 5). Concrete Work for Rigid Pavement at Crossing Road 1 & 3 | PIPE SUPPORT & PLATEFORM | 1). Monitoring & Inspection for Operating Platform Installation at Tank A30, R-6, P5, A4, A5 (Continue) 2). Monitoring & Inspection for Crossing Platform Installation at Tank R6, R5, A30 3). Witness Concrete Compressive Strength Test for Pipe Support & Operating Platform Foundation 4). Inspection for Concrete Work for Box Control at Crossing Road 3 (North Side) 5). Final Inspection for Fire Screen at Area Tank A-4 & A5 6). Final Inspection for Crossing Road at CR 1, 7, 8, 4
4 | Mochamad Johansyah | Stationary & Package Inspector | TANK D20-13A | 1). Monitor and observe finishing activity after pneumatic test: - Dismantle manhole cover - Welding visual installation foam dum plate 2). Attend for box up after painting process | TANK D20-13A | 1) Monitor and follow update continue work after Pneumatic Test until Box Up 2) Follow up ITR of the repair by contractor until review
|  |  | TANK A5 | 1). Monitor fabricate for roof accessories structure: - Welding visual inspection inner rafter | TANK A5 | 1) Monitor update any issue from Tank A5 after finished the work of contract
5 | Rachmad Suryadi | Stationary & Package Inspector | TANK T-900 | 1) Visual Welding Inspection Shell Plate 2) Fit Up Joint Inspection Shell Plate 3) Radiography of Joint Shell to Shell | TANK T-900 | 1) Visual Welding Inspection Shell Plate 2) Fit Up Joint Inspection Shell Plate 3) Radiography of Joint Shell to Shell 4) Monitoring & Surveillance Activity Modification Tank
6 | Friyudian Nata Kusuma | QAQC Engineer | All Area Non-Novasi | 1). Surveillance All Area Non-Novasi 2). QC Document • Monitoring dan koordinasi dengan PertaMC (PT.Kokoh Semesta) terkait percepatan closing document test Package Post Revamp • Review QC Document PT.PertaMC (OC-O) • Review QC Document PT.Ometraco 3). Weekly Meeting • Pekerjaan Site Work Pompa dan Retrofit Mechanical Seal G-3-17 A/B/C/D Serta Steam Turbin Penggerak GT-3-17 A/B/C/D • Pekerjaan Relokasi Oil Catcher-O (OC-O) dan Pompa Pengendali Banjir • Bi-Weekly Meeting Proyek Modifikasi Tangki | All Area Non-Novasi | 1). Surveillance All Area Non-Novasi 2). QC Document • Monitoring dan koordinasi dengan PertaMC (PT.Kokoh Semesta) terkait percepatan closing document test Package Post Revamp • Review QC Document PT.PertaMC (OC-O) • Review QC Document PT.Ometraco • Review QC Document PT.Agroasia Unit Inkaba, Rubber Bellow untuk Pekerjaan Project SWI 3). Weekly Meeting • Pekerjaan Site Work Pompa dan Retrofit Mechanical Seal G-3-17 A/B/C/D Serta Steam Turbin Penggerak GT-3-17 A/B/C/D • Pekerjaan Relokasi Oil Catcher-O (OC-O) dan Pompa Pengendali Banjir • Bi-Weekly Meeting Proyek Modifikasi Tangki
7 | Richard Messakh | QAQC Coordinator | All Area Non-Novasi
8 | Muslimin | Piping Inspector | POST REVAMP | 1). Review Documnet Test Package, Re-Instatement Test Package
|  |  | Unit 332 Area 6 UCT | 1). support TS team Monitoring indication external Corrosion at Lime Tank A-332-02-A3-D1A & A-332-02-A3-D1B. Consequences of minor chemical exposure. Will be action surface treatment with Buffing & Pickling
9 | Naufal Dzaky Muttqin Attamimi | Piping Inspector |  |  | POST REVAMP | 1). Review Document Test Package POSTREVAMP 2). Verification GJ (Golden Joint) Activity POSTREVAMP 3). MC Punch Clear POSTREVAMP"
10 | Bintang Ramadhan | Piping Inspector | POST REVAMP | 1). Witness inspection Punch Clear 2). Witness inspection Bolt Tightening 3). Witness inspection Re-instatement 4). Test Package Review | POST REVAMP | 1). Witness inspection Punch Clear 2). Witness inspection Bolt Tightening 3). Witness inspection Re-instatement 4). Test Package Review
|  |  | CDU IV & CDU | 1). Survillance Line Injection Water Carrier CDU IV & CDU Pre-flush | CDU IV & CDU | 1). Survillance Line Injection Water Carrier CDU IV & CDU Pre-flush
11 | Anggit Wijatmoko | Piping Inspector | POST REVAMP | 1). Test PKG Review 2). Re - Instatement 3). Monitoring Golden Joint 4). MC Punch Clearing | POST REVAMP | 1). Test PKG Review 2). Re - Instatement 3). Monitoring Golden Joint 4). MC Punch Clearing"
12 | Dadan Yudhi P | Mechanical Rotating Inspector | OC-O | 1). QC Document : - Review ITR Piping work Document - Review Radhiography Film test pipe 20" 34-OWS-003-20" B20 sheet 6 of 8 joint 2 2). Weekly Meeting : - Oil Cacher O Project Pengendali Banjir jl.104 3). Surveilance Monitoring : - Oil Cacher O Project Pengendali Banjir jl.104 Monitoring Test Pit and Crossroad pipe 20" 34-OWS-003-20" B20 sheet 6 of 8 - Holiday test wraping pipe 20" 34-OWS-003-20" B20 sheet 6 of 8 & 4" 34-OS-004-4"-B20 sheet 1 of 4 | OC-O | 1). QC Document : - Review ITR Piping work Document (sustain) - Review Radhiography Film test pipe 20" (continue this week) 34-OWS-003-20" B20 sheet 6 of 8 joint 2(continue this week) 2). Weekly Meeting : - Oil Cacher O Project Pengendali Banjir jl.104 (sustain) 3). Surveilance Monitoring : - Oil Cacher O Project Pengendali Banjir jl.104 Monitoring Test Pit and Crossroad pipe 20" 34-OWS-003-20" B20 sheet 6 of 8 (continue this week obstacle sika n/y approve) - Holiday test wraping pipe 20" 34-OWS-003-20" B20 sheet 6 of 8 & 4" 34-OS-004-4"-B20 sheet 1 of 4 (continue this week)
13 | Diyan Febiyanto | Mechanical Rotating Inspector | HCU_STEAM TURBINE GT-3-17 A/B/C/D | 1). QC Document - Review QC Document PT.Ometraco 2). Weekly Meeting - Pekerjaan Site Work Pompa dan Retrofit Mechanical Seal G-3-17 A/B/C/D Serta Steam Turbin Penggerak GT-3-17 A/B/C/D 3). urveillance/Monitoring - Pekerjaan Site Work Pompa dan Retrofit Mechanical Seal G-3-17 A/B/C/D Serta Steam Turbin Penggerak GT-3-17 A/B/C/D | HCU_STEAM TURBINE GT-3-17 A/B/C/D | 1). QC Document : - Review QC Document PT. Ometraco 2). Weekly Meeting : - Pekerjaan Site Work Pompa dan Retrofit Mechanical Seal G-3-17 A/B/C/D Serta Steam Turbin Penggerak GT-3-17 A/B/C/D 3). Surveillance/Monitoring : - Pekerjaan Site Work Pompa dan Retrofit Mechanical Seal G-3-17 A/B/C/D Serta Steam Turbin Penggerak GT-3-17 A/B/C/D
|  |  | POST REVAMP | 1) Painting Work & Insullation Monitoring Painting not Completely Dry/Cured on Post Revamp 2). Monitoring Painting Work on Piping Post Revamp (Tank R3) | OC-O | 1). QC Document : - Review QC Document PT. SAMI 2). Weekly Meeting : - Pekerjaan Relokasi Oil Cathcer-O (OC-O) dan Pompa Pengendali Banjir G-34-106A/B, G-34-107A/B & G-34-86A/B 3). Surveillance/Monitoring : - Pekerjaan Relokasi Oil Cathcer-O (OC-O) dan Pompa Pengendali Banjir G-34-106A/B, G-34-107A/B & G-34-86A/B
14 | Sutan Haris | Coating Inspector | POST REVAMP | 1). Monitoring Instal Hot insulation line 320-P-491A-10"-1CB2501-ST-65 2). Final Inspection Hot Insulation line : • M320-P-491A-10"-1CB2501-ST-65 line P-491 A (RFI No : TIPR-RFI-PMC-PI-0835 • M320-P-491A-10"-1CB2501-ST-65 line P-491 A (RFI No : TIPR-RFI-PMC-PI-0834 • M320-P-491A-10"-1CB2501-ST-65 line P-491 A (RFI No : TIPR-RFI-PMC-PI-0833 • M320-P-491A-10"-1CB2501-ST-65 line P-491 A (RFI No : TIPR-RFI-PMC-PI-0832 • M320-P-491A-10"-1CB2501-ST-65 line P-491 A (RFI No : TIPR-RFI-PMC-PI-0831 3). Touch up Painting POSTREVAMP- K0067/75-TP413-0001 Pipe Line P-413-8" from TP-224 to TP-223 ELBOW STILL BARE METAL AT JOINT 114 (Result : Posh poned , Painting Not Cure) | POST REVAMP | 1). Monitoring Instal Hot insulation line 320-P-491A-10"-1CB2501-ST-65 2). Final Inspection Hot Insulation line : • M320-P-491A-10"-1CB2501-ST-65 line P-491 A (RFI No : TIPR-RFI-PMC-PI-0830 • M320-P-491A-10"-1CB2501-ST-65 line P-491 A (RFI No : TIPR-RFI-PMC-PI-0834 • M320-P-491A-10"-1CB2501-ST-65 line P-491 A (RFI No : TIPR-RFI-PMC-PI-0835 • M320-P-491A-10"-1CB2501-ST-65 line P-491 A (RFI No : TIPR-RFI-PMC-PI-0836 • M320-P-491A-10"-1CB2501-ST-65 line P-491 A (RFI No : TIPR-RFI-PMC-PI-0837 3). Repair Painting upper Foating Roof Tank D 20 13 A 4) Closing Punch List affer Repair & Touch up Painting POSTREVAMP- K0067/75-TP413-0001 Pipe Line P-413-8" from TP-224 to TP-223 ELBOW STILL BARE METAL AT JOINT 114 (Result : Posh poned , Painting Not Cure)
15 | Boy Candra | Electrical Instrument Eng | CDU IV | 1). Weekly Meeting Pekerjaan Instrumentasi Recovery CDU IV* under PT. Andalas. | CDU IV | 1). Weekly Meeting Pekerjaan Instrumentasi Recovery CDU IV* under PT. Andalas.
|  |  | OC-O | 1). Weekly Meeting Based on contract No. SP-24182, related to the Oil Cather-O (OC-O) Relocation Work and Flood Control Pumps at RDMP RU-V Balikpapan. | OC-O | 1). Weekly Meeting Based on contract No. SP-24182, related to the Oil Cather-O (OC-O) Relocation Work and Flood Control Pumps at RDMP RU-V Balikpapan. 2). Monitoring Installation Support/Stanchion Cable Ladder & Lighting Pole at OC-O area jl. 103
|  |  | All AREA PANEL TEMPORARY | 1). Surveillance Monitoring & Control Potential Issue all of Panel Temporary | All AREA PANEL TEMPORARY | 1). Surveillance Monitoring & Control Potential Issue all of Panel Temporary
16 | Christyanto Manullang | Electrical Instrument Eng | All AREA PANEL TEMPORARY | Surveillance Temporary Panel in South and North - Monitoring panel in confined space without GFCI proposal letter - Monitoring comment QC for panel temporary - Monitoring E&I acativity in OC-O - Monitoring E&I acativity in HCU for Turbin Installation | All AREA PANEL TEMPORARY | Surveillance Temporary Panel in South and North - Monitoring panel in confined space without GFCI proposal letter - Monitoring comment QC for panel temporary - Monitoring E&I acativity in OC-O - Monitoring E&I acativity in HCU for Turbin Installation
|  |  | CDU IV | 1). Weekly Meeting Pekerjaan Instrumentasi Recovery CDU IV* under PT. Andalas. | CDU IV | 1). Weekly Meeting Pekerjaan Instrumentasi Recovery CDU IV* under PT. Andalas.
|  |  | OC-O | 1). Weekly Meeting Pekerjaan Oil Cather-O installation | OC-O | 1). Weekly Meeting Pekerjaan Oil Cather-O installation
17 | Nur Hidayani | QA Engineering | CIP | Business Trip to Jakarta Duration: 1 Week Activity: Attend and participate in CIP Forum | All Area Non-Novasi | 1. Review Dokumen - Dokumen Procedure dan compile Document 2. Review Dokumen Dossier Pekerjaan Jasa Instalasi Penambahan Fasilitas Pendukung Laboratorium Analisis Proyek 3. Review Dokumen Pemeriksaan Material Rubber Bellow dari Agronesia Inkaba Rubber Industry 4. Follow up dan Update W2 & W3 September 2026 – “Weekly Basis Highlight Issue Pekerjaan Non-Novasi RDMP RU V Balikpapan
18 | Defi Angelina | Document Control | OFFICE | Monitoring Document | OFIICE | 1). Monitoring Document OC-O for Civil 2). Monitoring Document OC-O for Piping 3). Monitoring document PDP for civil 4). Monitoring document administration all personil 5). Monitoring recap over time all personil 6). Monitoring daily report all personil 7). Request over time for saturday and sunday
19 | Bimo Habib | Document Control | OFFICE | Monitoring QC Document | OFFICE | Monitoring QC Document
20 | Arif Abdillah Harahap | Mechanical Rotating Inspector | HCU_STEAM TURBINE GT-3-17 A/B/C/D | 1). QC Document : - Review QC Document PT.Ometraco 2). Weekly Meeting : - Pekerjaan Site Work Pompa dan Retrofit Mechanical Seal G-3-17 A/B/C/D Serta Steam Turbin Penggerak GT-3-17 A/B/C/D 3). Surveillance/Monitoring : - Pekerjaan Site Work Pompa dan Retrofit Mechanical Seal G-3-17 A/B/C/D Serta Steam Turbin Penggerak GT-3-17 A/B/C/D | HCU | 1). QC Document : Review QC Document PT. Ometraco 2). Weekly Meeting : Pekerjaan Site Work Pompa dan Retrofit Mechanical Seal G-3-17 A/B/C/D Serta Steam Turbin Penggerak GT-3-17 A/B/C/D 3). Surveillance/Monitoring : Pekerjaan Site Work Pompa dan Retrofit Mechanical Seal G-3-17 A/B/C/D Serta Steam Turbin Penggerak GT-3-17 A/B/C/D
[5 empty] | OC-O | 1). Review QC Document PT. SAMI 2). Weekly Meeting Pekerjaan Relokasi Oil Cathcer-O (OC-O) dan Pompa Pengendali Banjir G-34-106A/B, G-34-107A/B & G-34-86A/B 3). 3). Surveillance/Monitoring : Pekerjaan Relokasi Oil Cathcer-O (OC-O) dan Pompa Pengendali Banjir G-34-106A/B, G-34-107A/B & G-34-86A/B
21 | M Mego Senatung | Piping Inspector | POST REVAMP | 1). Review Documnet Test Package 2). Re-Instatement Test Package 3). MC Punch Clear | POST REVAMP SOUTH Area | 1). Review Document Test Package POSTREVAMP 2). Verification GJ (Golden Joint) Activity POSTREVAMP 3). MC Punch Clear POSTREVAMP 4). Support Monitoring Tank A-5